## Sheet1
Features | Nb. hours | Features | Nb. hours | Features | Nb. hours | Compte Final | Hours
User Interface |  | Driver Interface |  | Admin Interface |  | User Interface | 600
Mapping System |  | Itinéraires | 50 | Admin Management | 50 | Driver Interface | 145
map integration | 25 | Reports | 20 | Driver Management | 50 | Admin Interface | 265
user locatiion | 10 | Cancellation | 20 | User Management | 50 | TOTAL | 1120
driver location | 10 | Destination | 50 | Payment Management | 50 | Coût Aprox | 50000
Payment |  | Driver Registration |  | Promotions | 40
Payment method | 60 | Login | 40 | Issue Management | 30 | 1 Developpeur | 40h/semaine
payment selection | 15 | Registration | 10 | Reviews Management | 30 | Temps Aprox | 28 semaine
User registrtion |  | Vehicule registration | 10 | Authorization | 10 | Ready by | Juin 2023
Registration | 10 | TOTAL | 200 | TOTAL | 310
Login | 50 |  |  |  |  | 2 Developpeur | 40h/semaine
Mot de passe oublié | 10 |  |  |  |  | Temps Aprox | 14 semaine
Notification | [5 empty] | Ready by | Mars 2023
SMS | 30
Notification | 40 |  |  |  |  | 4 Developpeur | 40h/semaine
Cost Estimation | [5 empty] | Temps Aprox | 7 semaine
Estimation du voyage | 30 |  |  |  |  | Ready by | Fevrier
Split le coût | 100
UI Design
IOS design | 120
Andoid design | 100
TOTAL | 610